## Instructions
Activities During the Planning Meet:
| Estimated Task Priority: | Each team member select a value between 0 (most unimportant) to 10 (most important) from the drop down list based on his/her own understanding about the task.
| Estimated Task Difficulty: | Each team member select a value between 0 (extremely easy) to 10 (extremely difficult) from the drop down list based on his/her own understanding about the task.
| Estimated Task Time Required: | Each team member select a value between 1 to 14 days from the drop down list based on his/her own understanding about the task.
| Confidence about the Task: | Each team member select a value between 0 (not confident at all) to 10 (extremely confident) from the drop down list based on his/her own understanding about the task and his/her own capabilities.
| Assignee's Mood: | Excited | Happy | Neutral | Sad | Depressed
| Task Assignee: | Team members should discuss among themselves to distribute the tasks. If there are tasks which remain unassigned after the discussion, team lead will decide to whom the remaining task(s) should be delegated.
Activities During the Subsequent Planning Meeting
Review for each task: if it has been completed (Yes/No), rate the quality of the result (0: Extremely Bad -10: Excellent)

## Team Meeting
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Mohika Kataruka | Jerral Chua Fung Yong | Jethani Samarth | Sinha Armaan | Jain Sparsh | Faye Chan | Lai Yi
Team member's mood during the this week's meeting: |  |  | Neutral | Neutral | Happy | Neutral | Neutral | Neutral | Neutral
1 | System Requirement Specification Document | Task Quality Evaluation (After Task Completed) | 10 | 10 | 9 | 9 | 10 | 9 | 9 | 10 | 8 | 9.8571 | Mohika Kataruka | Jerral Chua Fung Yong Mohika Kataruka Jain Sparsh | Allocated by Team Leader | Yes | 12 day | Happy | 9.4286
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 7 | 8 | 8 | 9 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 10 | 12 | 9 | 9 | 10 | 10 | 9
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 10 | 10 | 10 | 9 | 8
2 | Quality Plan Document | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 9 | 9 | 9 | 9 | 9.2857 | 8.1429 | 7.4286 | Mohika Kataruka | Jethani Samarth Sinha Armaan Faye Chan Lai Yi | Through Discussion | Yes | 12 days | Happy | 9.1429
| Estimated Task Priority（0-10） |  | 10 | 8 | 9 | 9 | 10 | 10 | 9
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 8 | 8 | 9 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 10 | 10 | 5 | 7 | 10 | 9 | 1
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 10 | 10 | 9 | 8 | 7
3 | Update Project Proposal and Use Case Document | Task Quality Evaluation (After Task Completed) | 9 | 8 | 8 | 9 | 9 | 9 | 8 | 7.2857 | 3 | 2.8571 | Mohika Kataruka | Mohika Kataruka | Through Discussion | Yes | 2 days | Happy | 8.5714
| Estimated Task Priority（0-10） |  | 8 | 4 | 8 | 7 | 9 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 2 | 2 | 3 | 4 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 3 | 4 | 4 | 2 | 2 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 9 | 9 | 9
4 | Update Use Case Diagram | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 9 | 10 | 8 | 8 | 7.2857 | 3 | 2.8571 | Mohika Kataruka | Jerral Chua Fung Yong | Through Discussion | Yes | 2 days | Happy | 9.1429
| Estimated Task Priority（0-10） |  | 8 | 4 | 8 | 7 | 9 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 2 | 2 | 4 | 3 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 3 | 4 | 4 | 2 | 2 | 3
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 10 | 10 | 9 | 9 | 8
5 | Update Team Backlog | Task Quality Evaluation (After Task Completed) | 8 | 10 | 9 | 9 | 9 | 9 | 8 | 6.4286 | 2.5714 | 2.8571 | Mohika Kataruka | Jerral Chua Fung Yong Mohika Kataruka Jethani Samarth Sinha Armaan Jain Sparsh Faye Chan Lai Yi | Through Discussion | Yes | 3 days | Happy | 8.8571
| Estimated Task Priority（0-10） |  | 7 | 4 | 8 | 7 | 6 | 6 | 7
| Estimated Task Difficulty（0-10） |  | 2 | 4 | 2 | 2 | 3 | 2 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 3 | 4 | 4 | 2 | 1 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10 | 9
6 | Update Trello | Task Quality Evaluation (After Task Completed) | 8 | 10 | 10 | 10 | 10 | 9 | 8 | 3 | 2 | 2.1429 | Mohika Kataruka | Jerral Chua Fung Yong Mohika Kataruka Jethani Samarth Sinha Armaan Jain Sparsh Faye Chan Lai Yi | Through Discussion | Yes | 5 days | Happy | 9.2857
| Estimated Task Priority（0-10） |  | 5 | 3 | 2 | 2 | 3 | 3 | 3
| Estimated Task Difficulty（0-10） |  | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 2 | 2 | 2 | 2 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 9 | 8